## VA-VAEC
[6 empty] | VA SOP |  |  | VAEC
[6 empty] | (official) |  |  | (Cognosante)
Cloud-Based VA Application ATO Process | [5 empty] | Appendix A |  |  |  | assigned
PHASE | TASK | DESCRIPTION | REQ'D | ARTIFACT | TARGET | VA SOP | ASSIGNED | DUE(DONE)
Cloud ATO | RV Entry | RiskVision Entry of cloud-based VA application | Y |  | RV | Appendix A
| App Q&A | CSP / VA Applicaiton questionnaire | Y |  | RV | Appendix A | SyO / ISO
| CRSP | Customer Responsibilities Security Plan | Y |  | RV | Appendix A | SyO / ISO
On-premises VA Application ATO Process
PHASE | TASK | DESCRIPTION | REQ'D | ARTIFACT | TARGET | VA SOP | ASSIGNED | DUE(DONE)
Pre-Requisites | ISO designation | Information Security Officer Designation | Y | person |  | 3.1 |  |  | 5.1 | ?EMPO Information Assurance (IA) Security Analyst
| RV Entry | RiskVistion System Inventory Checklist | Y | doc | RV | 3.2 |  |  | 5.3
Registration | App Reg | Application Registration | Y | doc |  | 4.1.1 |  |  | 5.4
Security Docs | SSP | System Security Plan | Y | doc | RV | 4.2.1 |  |  | 6.1.1
| MASA | Minor Application Self Assessment | N | doc | RV | 4.2.2
| SA | Signatory Authority | CRSP | doc |  | 4.2.3 |  |  | 6.1.8
| RA | Risk Assessment | CRSP | doc |  | 4.2.4 |  |  | 6.1.10
| CMP | Configuration Management Plan | CRSP | doc | RV | 4.2.5 |  |  | 6.1.7
| IRP | Incident Response Plan | CRSP | doc | RV | 4.2.6 |  |  | 6.1.2
| ISCP | Informaton Security Contingency Plan | CRSP | doc | RV | 4.2.7 |  |  | 6.1.4
| DRP | Disaster Recovery Plan | CRSP | doc | RV | 4.2.8 |  |  | 6.1.3
| PIA | Privacy Impact Assessment | CRSP | doc | RV | 4.2.9 |  |  | 5.6
| ISA / MOU | Interconnection Security Agreeement / Memorandum of Understanding | CRSP | doc | RV | 4.2.10 |  |  | 6.1.6
| SDR | Secure Design Review | CRSP | doc |  | 4.2.11 |  |  | 5.5
| RA | Risk Assessment | CRSP | doc |  | 4.2.4 |  |  | 6.1.10
Request as soon as possible after CRISP compliance
Technical / Testing | Nessus scan | Nessus scan | Y | scan | RV (TVM) | 4.3.1 |  |  | 6.2.1
| DB scan | Database scan | Y | scan |  | 4.3.1.1 |  |  | 6.2.2 | if contains a database
| QCR (V&V) | Quaility Code Review (Verification & Validation) | Y | code |  | 4.3.2 |  |  | 6.2.3
| SCR | Secure Code Review | Y | code |  | 4.3.3 |  |  | 6.2.4 | use VA static code analysis tools (M not supported; manual review)
| PT / AA | Penetration Test / Application Assessment | Y | code |  | 4.3.4
| SCCD | Security Configuration Compliance Data | Y |  |  | 4.3.5 |  |  | 6.2.6
| SCA | Security Control Assessment | Y | code |  | 4.3.6
| CIE | Control Implementation Evidence | Y | doc |  | 4.3.7 |  |  | 6.1.9
| EDS | Enterprise Discovery Scan | Y |  |  | 4.3.8
OTHER | POA&M | Plan of Action and Milestone Remediation |  | ?? |  |  |  |  | 6.3
| AOSB | Authorizing Official System Brief |  | doc? |  |  |  |  | 6.4
| VIPR ID | Veteran Integrated Process Request ID |  | doc |  |  |  |  | 5.2
| PT / WASA | Penetration Test / Web Application Security Assessment |  | code |  |  |  |  | 6.2.5